## Slide 1: Development of wireless Sensor Node for urban agriculture

## Slide 2: Objective
compare and contrast zigbee(802.15.4) and wifi(802.11) communication protocol to find an optimal solution for urban agriculture setup on Terrace
what to compare
  power consumption
  range
  scalability factor
  cost
Design working sensor node that can be developed on terrace or similar environment
Develop a backbone with sensor node and test strategies to carry out future study on different hardware and other communication module
Notes: scalability - option to add sensors in future, easy to program
  communication protocol
  topology
  hardware
  stability
  power options

## Slide 3: Requirement
Hardware
  MSP430f5529
  Temperature+humidity sensor
  Zigbee module - cc2530
  wifi - ESP8266
  Batteries
MSP430 microcontroller
cc2530 with SMA antenna
ESP8266 Wifi module

## Slide 4: Test Strategies
Power Consumption
  Lab test - check power consumption using DMM/DSO
  In field test - Measure battery voltage, deploy sensor for duration of 24 hours and log sensor reading, measure battery voltage again.
Range
  Deploy sensors at farthest location/max. theoretical range suggested in datasheet. Log sensor reading to ensure no data loss is occurring.
  Deploy multiple sensor nodes at strategic locations to check effect of obstructions
Scalability
  Effect of adding/removing nodes on data transmission and power consumption

## Slide 5: Milestone
Reading about protocols and existing work in this field
UART communication on MSP430
using TI Z-stack API to connect cc2530 with MSP430
Test zigbee based sensor node in lab ( 13/03)
Deploy sensors on terrace to test log sensor data (19/03)
interface esp8266 with MSP430 (31/03)
Test wifi based sensor node in lab (31/03)
Deploy sensors on terrace to test log sensor data (02/04)
Obtain result based on data (16/04)

## Slide 6: Choosing right hardware
Embedded Multi-chip sensor nodes
  Microcontroller, transceiver, sensor and power supply
System-on-chip sensor nodes
  On-chip controller and transceiver
Consideration factor
  Peripheral features to attach sensors
  power consumption
  memory
  cost

## Slide 7: Factors to be considered
Area
Power options available
sensor requirement

## Slide 8: Range vs Data Rate comparison
Source: www.embedur.com

## Slide 9: Wireless Communication
Zigbee
  802.15.4,
  250 kbps @2.4 GHz
  low-cost
  energy efficient
  Support Mesh topology
  100m - 1.5Km
Wifi
  802.11
  2-54 Mbps @2.4 GHz
  low-cost
  high energy consumption
  Only Star
  100m

## Slide 10: Network Layers
Zigbee Protocol Layers
derived from OSI model

## Slide 11: Network architecture for agriculture applications
Stationary
  sensor nodes are deployed at a fixed position (example: temperature, moisture, wind speed etc)
Mobile
  devices changes position with time (example: network of drones, farmer carrying sensor/cell phone)
Hybrid
  mix of Stationary and mobile
What is our requirement: Stationary

## Slide 12: Types of sensor nodes
WSNs are deployed on land, underground and underwater
5 types
  Terrestrial WSN
  underground WSN
  underwater WSN
  multi-media WSN
  mobile WSN
Notes: Resource: WSN survey paper
Multi-media WSNs: enable monitoring and tracking of events in the form of multimedia such as video, audio, and imaging. consist of a number of low cost sensor nodes equipped with cameras and microphones.

## Slide 13: Zigbee Network topology

## Slide 14: To buy
MSP430f5529 - 8 -Rs. 1384
CC2530 - 5 -Rs. 949
Nodemcu - 5

## Slide 15
Intelligent decision making capability
  multihop